## Sheet1
Camunda -Work Breakdown Structure
S.no | Task Description | Planned StartDate | Planned EndDate | Actual Start Date | Actual End Date | Efforts in Hours | Assigned To | Status
Vendor Management System
S.no | Sprint - 1 | 2023-04-03
1 | Project Setup | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 | 8hrs
Local Machine
GIT Setup
2 | SaaS Camunda Configuration | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-04-05 | 3hrs
Set up and configure the Camunda BPM platform on the cloud infrastructure
3 | Process Modeling and Design

## Sheet2
Camunda CoE
S.No | Use Case | Task Description | Start Date | End Date | Resource Involved | Efforts in Hours
1 | VMS | Project setup | 03.04.2023 | 03.04.2023 | Kannan,Rajesh | 8
|  | Set up and configure the Camunda BPM platform on the cloud infrastructure | 04.04.2023 | 05.04.2023 | Kannan,Rajesh | 16
|  | Saas Camunda configuration | 06.04.2023 | 10.04.2023 | Kannan,Rajesh | 24 | Saturday and Sunday leave
|  | Process modeling and Design | 11.04.2023 | 11.04.2023 | kannan | 8
|  | Exposing Api's | 12.04.2023 | 15.04.2023 | kannan | 32
|  | Working on Frontend using HTML,Bootstrap | 05.04.2023 | 12.04.2023 | AshokKumar & Hariharan | 48 | Saturday and Sunday leave
|  | Integration | 13.04.2023 | 15.04.2023 | Rajesh, AshokKumar & Hariharan | 24
| Cypress Interview Preparation |  | 17.04.2023 | 02.05.2023 | AshokKumar, Kannan and Rajesh | 96
Hariharan went to Wondersoft
2 | Order Fulfilment | Saas Camunda configuration | 03.05.2023 | 04.05.2023 | Rajesh | 16
|  | Process modeling and Design | 05.05.2023 | 08.05.2023 |  | 24
|  | Exposing Api's | 09.05.2023 | 18.05.2023 |  | 64
|  | writing worker for order fulfilment | 19.05.2023 | 20.05.2023 |  | 16
|  | Assisting with the integration process for the React team. |  |  |  | 64
3 | Customer Onboarding Process for Insurance | Saas Camunda configuration | 03.05.2023 | 03.05.2023 | Kannan | 8
|  | Process modeling and Design | 04.05.2023 | 06.05.2023 |  | 24
|  | Designing DMN | 08.05.2023 | 09.05.2023 |  | 16
|  | Exposing Api's | 10.05.2023 | 17.05.2023 |  | 48
|  | Writing worker | 18.05.2023 | 19.05.2023 |  | 16
|  | Working on Frontend using HTML,Bootstrap | 03.05.2023 | 20.05.2023 | Ashok Kumar | 120
4 | Banking Customer Onboarding | Gathering requirements for a banking use case | 01.06.2023 | 03.06.2023 | Rajesh | 24
|  | Saas Camunda configuration | 05.06.2023 | 06.06.2023 |  | 16
|  | Process modeling and Design | 2023-06-07 | 09.06.2023 |  | 24
|  | Designing DMN | 12.06.2023 | 14.06.2023 |  | 24
|  | Exposing Api's | 15.06.203 | 22.06.2023 |  | 56
5 | Procurement | Gathering requirements for a banking use case | 22.05.2023 | 23.05.2023 | Kannan | 16
|  | Saas Camunda configuration | 24.05.2023 | 24.05.2023 |  | 8
|  | Process modeling and Design | 25.05.2023 | 29.05.2023 |  | 24
|  | Microservice Preparation | 30.05.2023 | 03.06.2023 |  | 40
|  | Designing DMN | 05.06.2023 | 07.06.2023 |  | 24
|  | Exposing Api's | 08.06.2023 | 15.06.2023 |  | 48
|  | Writing worker | 16.06.2023 | 22.06.2023 |  | 40
6 | Loan Processing | Gathering requirements for a banking use case | 12.06.2023 | 14.06.2023 | Ashok Kumar | 24
|  | Saas Camunda configuration | 15.06.2023 | 16.06.2023 |  | 16
|  | Process modeling and Design | 17.06.2023 | 22.06.2023 |  | 40